## Sheet1
Estimate |  | Siliguri Municipal Corporation
|  | Estimate for: | [8 empty] | 9New prakesh Nager)
|  | type-f,Constructi0n of Public Toilet near Vishal cinema hall (Lower Vanu Nager)ward no-43 | [9 empty] | 9unit-1 | 9Unit-1 | 0(
All Linear measurements are in metre
Schedule ref. | Item Number | Description of Item |  |  |  |  | Quantity |  | Rate | Unit | Amount Rs.
|  | Member | Number | Length | Breadth | Height
.
PWD(WB)/BUILDING WORKS/Page-1/Item-2
1.2 | 1 | Earth work in excavation of foundation trenches or drains in all sorts of soil (including mixed soil but excluding laterite or sand stone) including removing, spreading or stacking the spoils within a lead of 75m. as directed. The item includes necessary trimming the sides of trenches, levelling, dressing and ramming the bottom, bailing out water as required complete. .
1.2.a | 1.01 | (a) Depth of excavation not exceeding 1.500 mm.
|  |  | 4 | 1.2 | 1.2 | 1 | 5.76 | Cu.M
|  |  | 1 | 1 | 0.375 | 0.15 | 0.06 | Cu.M
[6 empty] | Total | 5.82 | Cu.M | 11927 | % Cu.M. | 694.15
PWD(WB)/BUILDING WORKS/Page-1/Item-3
1.3 | 2 | Earth work in filling in foundation trenches or plinth with good earth in layers not exceeding 150 mm. including watering and ramming etc.layer by layer complete .(payment to be made on the basis of measurement of finished quantity of work).
1.3.a | 2.01 | (a) With earth obtained from excavation of foundation.
|  |  | 4 | 1.2 | 1.2 | 1 | 5.76 | Cu.M
|  |  | 1 | 1 | 0.375 | 0.15 | 0.056 | Cu.M
[6 empty] | Total | 5.816 | Cu.M | 7754 | % Cu.M. | 450.97
PWD(WB)/BUILDING WORKS/Page-2/Item-4A
2.4A | 3 | (A) Filling in foundation or plinth by silver sand in layers not exceeding 150 mm. as directed and consolidating same by thorough saturation with water ramming complete . Including the cost of supply of sand .(payment to be made on measurement of finished quantity).
|  |  | 1 | 4.85 | 2.825 | 0.325 | 4.453 | Cu.M
[6 empty] | Total | 4.453 | Cu.M | 52107 | % Cu.M. | 2320.32
PWD(WB)/BUILDING WORKS/Page-14/Item-1
14.1 | 4 | Single brick flat soling of picked jhama bricks including ramming and dressing bed to proper level and filling joints with local sand.
|  |  | 4 | 1.2 | 1.2 |  | 5.76 | Sq.M
|  |  | 2 | 2.5 | 0.375 |  | 1.875 | Sq.M
|  |  | 1 | 1 | 0.375 |  | 0.375 | Sq.M
|  |  | 1 | 4.85 | 2.825 |  | 13.701 | Sq.M
[6 empty] | Total | 21.711 | Sq.M | 324 | Sq.M. | 7034.36
PWD(WB)/BUILDING WORKS/Page-26/Item-10
26.10 | 5 | Ordinary cement concrete (mix 1:1.5:3) with graded stone chips (20mm nominal size) excluding shuttering and reinforcement, if any, in ground floor as per relevant codes.
26.10.ii | 5.01 | (ii) River bazree.
|  |  | 4 | 1.2 | 1.2 | 0.15 | 0.864 | Cu.M
|  |  | 4 | 0.725 | 0.725 | 0.2 | 0.421 | Cu.M |  |  |  |  | 0
|  |  | 4 | 0.25 | 0.25 | 3.25 | 0.813 | Cu.M
|  |  | 2 | 4.6 | 0.25 | 0.25 | 0.575 | Cu.M
|  |  | 3 | 2.325 | 0.25 | 0.25 | 0.436 | Cu.M
|  |  | 2 | 2.325 | 0.25 | 0.15 | 0.174 | Cu.M
|  |  | 1 | 5.15 | 3.125 | 0.125 | 2.012 | Cu.M
[6 empty] | Total | 5.295 | Cu.M | 4745 | Cu.M | 25124.78
PWD(WB)/BUILDING WORKS/Page-23/Item-1
23.1 | 6 | Cement concrete with graded jhama khoa (30 mm size) excluding shuttering. In ground floor and foundation.
23.1.a | 6.01 | (a) 1:3:6 proportion.
|  |  | 4 | 1.2 | 1.2 | 0.1 | 0.576 | Cu.M
|  |  | 2 | 2.5 | 0.375 | 0.1 | 0.188 | Cu.M
|  |  | 2 | 1.5 | 1 | 0.1 | 0.3 | Cu.M
|  |  | 1 | 4.85 | 2.825 | 0.1 | 1.37 | Cu.M
[6 empty] | Total | 2.434 | Cu.M | 4298 | Cum. | 10461.33
PWD(WB)/BUILDING WORKS/Page-47/Item-1
47.1 | 7 | 25mm. thick damp proof course with cement concrete withstone chips (1:1.5:3) [with graded stone aggregate 10 mmnominal size] and admixture of water proofing compound asper manufacturer's specification followed by two coat ofpolymer based paint, (1st coat after 4 to 5 days of concretelaying and 2 nd coat just before brick masonry work) asdirected (cost of water proofing compound & polymer basedpaint to be paid separately).( Chequering not required overconcrete or painted surface).[Note: - Waterproofing as per item 9, polymer based paint asper item 8 (a) of subhead C of Section (C).
|  |  | 2 | 4.85 | 0.25 |  | 2.425 | Sq.M
|  |  | 3 | 2.825 | 0.25 |  | 2.119 | Sq.M
[6 empty] | Total | 4.544 | Sq.M | 196 | Sq.M. | 890.62
PWD(WB)/BUILDING WORKS/Page-16/Item-16
16.16 | 8 | 125 mm. thick brick work with 1st class bricks in cement mortar (1:4) in ground floor.
|  |  | 5 | 1.2 | 3 |  | 18 | Sq.M
|  |  | 3 | 1 | 3 |  | 9 | Sq.M
[6 empty] | Total | 27 | Sq.M | 674 | Sq.M. | 18198
PWD(WB)/BUILDING WORKS/Page-47/Item-3
47.3 | 9 | Supplying and laying Polythene Sheet (150gm / sq.m.) overdamp proof course or below flooring or roof terracing or infoundation or in foundation trenches.
|  |  | 2 | 5.14 | 3.125 |  | 32.125 | Sq.M
|  |  | 4 | 1.2 | 1.2 |  | 5.76 | Sq.M
[6 empty] | Total | 37.885 | Sq.M | 24 | Sq.M. | 909.24
PWD(WB)/BUILDING WORKS/Page-42/Item-36
42.36 | 10 | Hire and labour charge for shuttering with centreing and necessary staging up to 4 m. using approved stout props and thick hard wood planks of approved thick ness with required bracing for concrete slabs, beams, columns, lintels curved or staight including fitting fixing and striking out after complection of works. (up to roof of ground floor).
43.36.f | 10.01 | (f) 25mm. To 30mm. Shuttering with out staging in foundation etc.
|  |  | 4 | 4.85 | 0.25 |  | 4.85 | Sq.M
|  |  | 4 | 2.825 | 0.25 |  | 2.825 | Sq.M
|  |  | 16 | 1.2 | 0.15 |  | 2.88 | Sq.M
[6 empty] | Total | 10.555 | Sq.M | 205 | Sq.M. | 2163.78
PWD(WB)/BUILDING WORKS/Page-42/Item-36
42.36 | 11 | Hire and labour charge for shuttering with centreing and necessary staging up to 4 m. using approved stout props and thick hard wood planks of approved thick ness with required bracing for concrete slabs, beams, columns, lintels curved or staight including fitting fixing and striking out after complection of works. (up to roof of ground floor).
42.36.a | 11.01 | (a) 25 mm. to 30 mm. thick wooden shuttering as per decision & direction of the Engineer-in-charge. .
|  |  | 1 | 5.15 | 3.125 |  | 16.094 | Sq.M
|  |  | 2 | 8.275 | 0.125 |  | 2.069 | Sq.M
|  |  | 4 | 0.325 | 3 |  | 3.9 | Sq.M
|  |  | 4 | 4.85 | 0.125 |  | 2.425 | Sq.M
|  |  | 4 | 2.825 | 0.125 |  | 1.413 | Sq.M
[6 empty] | Total | 25.901 | Sq.M | 328 | Sq.M. | 8495.53
PWD(WB)/BUILDING WORKS/Page-48/Item-6
48.6 | 12 | Artificial stone in floor, dado, staircase etc. with cement conctrete (1:2:4) with stone chips laid in panels as directed with topping made with ordinary or white cement (as necessary) and marble dust in proportion (1:2) including smooth finishing and rounding off corners including raking out joints or roughening of concrete surface and application of cement slurry before flooring works, using cement @ 1.75 kg./sq.m. all complete including all materials and labour In ground floor. 3 mm. thick topping (High polishing grinding on this item is not permitted) with ordinary cement. Using grey cement.
48.6.ii | 12.01 | (ii) 25 mm. thick.
|  |  | 1 | 4.85 | 2.825 |  | 13.701 | Sq.M
[6 empty] | Total | 13.701 | Sq.M | 270 | Sq.M. | 3699.27
PWD(WB)/BUILDING WORKS/Page-43/Item-40
43.40 | 13 | Reinforcement for reinforced concrete work in all sorts of structures including distribution bars, stirrups, binders etc. initial straightening and removal of loose rust (if necessary), cutting to requisite length, hooking and bending to correct shape, placing in proper position and binding with 16 gauge black annealed wire at inter-section, complete as per drawing and direction.
44.40.a | 13.01 | (a) For works in foundation, basement and up to roof of ground floor/up to 4m. Tor steel/Mild steel.
44.40.a.i | 13.02 | SAIL/ TATA/RINL
Volumetric percentage calculation of reinforcefment
|  | Description |  |  |  |  | Volume of cc
|  | Total volume |  |  |  |  | 5.295 | cum
|  | Percentage of steel |  | 1.5 | %
|  | Weight of steel |  | 7.85 | MT/cum | Total
|  | Reinforcement by volume of CC | (5.295.00*1.5*7.85)/100 |  |  |  | 0.62 | MT
[6 empty] | Total | 0.62 | MT | 66502 | M.T. | 41231.24
PWD(WB)/BUILDING WORKS/Page-106/Item-18
106.18 | 14 | Collapsible gate with 40 mm.X 40mm x 6 mm.Tee as top and bottom guide rail, 20 mm,X10 mm,X2 mm. vertical channels 100 mm. apart in fully stretched position 20 mm. X5 mm.M.S. flats as collapsible bracing properly rivetted and washered including 38 mm. steel rollers including locking arrangement, fitted and fixed in position with lugs set in cement concrete and including cutting necessary holes, chasing etc. in walls , floors etc. and making good damages complete. (Add extra @1% for each addl. floor upto 5th floor and @1.25% for each addl. floor above 5th floor.)In ground floor. .
|  |  | 2 | 1 | 2.1 |  | 4.2 | Sq.M
[6 empty] | Total | 4.2 | Sq.M | 4351 | Sq.M. | 18274.2
PWD(WB)/BUILDING WORKS/Page-15/Item-7
15.7 | 15 | Brick work with 1st class bricks in cement mortar (1:4)
15.7.a | 15.01 | In foundation and plinth
|  |  | 2 | 4.85 | 0.25 | 0.6 | 1.455 | Cu.M
|  |  | 3 | 2.825 | 0.25 | 0.6 | 1.271 | Cu.M
|  |  | 2 | 2.5 | 0.25 | 0.6 | 0.75 | Cu.M
|  |  | 2 | 1 | 0.5 | 0.3 | 0.3 | Cu.M
[6 empty] | Total | 3.776 | Cu.M | 5172 | Cum. | 19529.47
PWD(WB)/BUILDING WORKS/Page-15/Item-7
15.7 | 16 | Brick work with 1st class bricks in cement mortar (1:4)
15.7.b | 16.01 | In Super structure, ground floor.
|  |  | 2 | 4.85 | 0.25 | 3 | 7.275 | Cu.M
|  |  | 3 | 2.825 | 0.25 | 3 | 6.356 | Cu.M
[6 empty] | Total | 13.631 | Cu.M | 5395 | Cum. | 73539.25
PWD(WB)/BUILDING WORKS/Page-189/Item-1
189.1 | 17 | Plaster ( to wall, floor, ceiling etc.) with sand and cement mortar including rounding off or chamfering conrners as directed and raking out joints including throating, nosing and drip course, scaffolding/staging where necessary (ground floor). [Excluding cost of chipping over concrete surface].
189.1.ii | 17.01 | (ii) With 1:4 cement mortar .
189.1.ii.b | 17.02 | (b) 15 mm. thick plaster.
|  |  | 2 | 7.675 | 3.75 |  | 57.563 | Sq.M
|  |  | 2 | 7.675 | 3 |  | 46.05 | Sq.M
|  |  | 2 | 2.325 | 3 |  | 13.95 | Sq.M
|  |  | 4 | 1.6 | 3 |  | 19.2 | Sq.M
[6 empty] | Total | 136.763 | Sq.M | 157 | Sq.M. | 21471.79
PWD(WB)/BUILDING WORKS/Page-189/Item-1
189.1 | 18 | Plaster ( to wall, floor, ceiling etc.) with sand and cement mortar including rounding off or chamfering conrners as directed and raking out joints including throating, nosing and drip course, scaffolding/staging where necessary (ground floor). [Excluding cost of chipping over concrete surface].
189.1.ii | 18.01 | (ii) With 1:4 cement mortar .
189.1.ii.c | 18.02 | (c)10 mm. thick plaster.
|  |  | 1 | 4.85 | 2.85 |  | 13.823 | Sq.M
[6 empty] | Total | 13.823 | Sq.M | 126 | Sq.M. | 1741.7
PWD(WB)/BUILDING WORKS/Page-192/Item-15
192.15 | 19 | Neat cement punning about 1.5mm thick in wall, dado, windowsill, floor etc.NOTE:Cement 0.152 cu.m per100 sq.m.
|  |  | 2 | 7.675 | 0.75 |  | 11.513 | Sq.M
[6 empty] | Total | 11.513 | Sq.M | 34 | Sq.M. | 391.44
PWD(WB)/BUILDING WORKS/Page-115/Item-3
115.3 | 20 | Supplying, fitting and fixing fibre reinforced polymer (FRP) Composite doorframe as per approved section with glass fibre reinforced plastic moulded skinsand a special sandwich core, so as to impart monolitaheic composite structure asper approved technology of Department of Science and Technology (DST) tosafisfy IS: 4020 door testing performance criteria..
115.3.i | 20.01 | (i) 66mm x 90mm
|  |  | 2 | 4.95 |  |  | 9.9 | M
[6 empty] | Total | 9.9 | M | 497 | Mtr. | 4920.3
PWD(WB)/BUILDING WORKS/Page-125/Item-14
125.14 | 21 | Supplying, fitting & fixing fibre reinforced polymer (FRP) Composite doorshutters as per approved design with glass fibre reinforced plastic moulded skinsand a special sandwich core, so as to impart monolitaheic composite structure asper approved technology of Department of Science and Technology (DST) tosatisfy IS:4020 door testing performance criteria.In ground floor.
125.14.ii | 21.01 | (ii) 25 mm thick
|  |  | 2 | 2.1 | 0.75 |  | 3.15 | Sq.M
[6 empty] | Total | 3.15 | Sq.M | 2581 | Sq.M. | 8130.15
PWD(WB)/BUILDING WORKS/Page-144/Item-26
144.26 | 22 | Anodise aluminium barred/tower/socket bolt (full covered) of approved manufactured from extruded section conforming to I.S.204/74 fitted and Fixed with cadmium plated screws:.
144.26.vii | 22.01 | (vii) 225 mm long x 10 mm dia. bolt.
|  |  | 5 |  |  |  | 5 | No.
[6 empty] | Total | 5 | No. | 84 | Each | 420
PWD(WB)/BUILDING WORKS/Page-140/Item-5
140.5 | 23 | Iron butt hinges of approved quality fitted and fixed with steel screws, with ISI mark.
140.5.viii | 23.01 | (viii) 100 mm x 75mm x 3.50 mm.
|  |  | 15 |  |  |  | 15 | No.
[6 empty] | Total | 15 | No. | 66 | Each | 990
PWD(WB)/BUILDING WORKS/Page-146/Item-31
146.31 | 24 | Anodised aluminium decorative handle (hexagonal / fluted) of approved quality fitted and fixed complete.
146.31.i | 24.01 | (i) 150 mm plate x 10 mm. dia rod x 12 mm. hexagonal/flutted.
|  |  | 10 |  |  |  | 10 | No.
[6 empty] | Total | 10 | No. | 87 | Each | 870
PWD(WB)/BUILDING WORKS/Page-141i/Item-10
141i.10 | 25 | (i) Iron hasp bolt of approved quality fitted and fixed complete (oxidised) with 16 mm dia rod with centre bolt and round fitting.
142i.10.b | 25.01 | (b) 250 mm long.
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 159 | Each | 636
PWD(WB)/BUILDING WORKS/Page-74/Item-46
74.46 | 26 | Supplying and laying chequered tiles of any shade & ofapproved quality with (1:1½:3) cement concrete laid in panelsor patterns as directed in pavement, footpath etc. includingnecessary underlay 25 mm thick [avg] cement mortar (1:3)complete in all respect with all labour and materials. [Usingcement slurry @ 4.4 kg/Sq.m at back side and @2.4 kg/Sq.mfor joint filling] Red Variety
74.46.i | 26.01 | (i) 25 mm. thick
|  |  | 1 | 2 | 1 |  | 2 | Sq.M
|  |  | 1 | 1 | 2.125 |  | 2.125 | Sq.M
[6 empty] | Total | 4.125 | Sq.M | 467 | Sq.M. | 1926.38
PWD(WB)/BUILDING WORKS/Page-198a/Item-5
198a.5 | 27 | Rendering the Surface of walls and ceiling with White Cement baseWATER PROOF wall putty of approved make & brand.(1.5 mm thick)
|  |  | 2 | 7.675 | 3.75 |  | 57.563 | Sq.M
|  |  | 2 | 7.675 | 3 |  | 46.05 | Sq.M
|  |  | 2 | 2.325 | 3 |  | 13.95 | Sq.M
|  |  | 4 | 1.6 | 3 |  | 19.2 | Sq.M
|  |  | 1 | 4.85 | 2.85 |  | 13.823 | Sq.M
[6 empty] | Total | 150.586 | Sq.M | 122 | Sq.M. | 18371.49
PWD(WB)/BUILDING WORKS/Page-195/Item-7
195.7 | 28 | Applying interior grade acrylic primer of approved quality and brand on plastered or concrete surface old or new surface to received distemper /Acrylic emulsion paint including scraping and preparing the surface thoroughly , complete as per manufactured specification and as per directions of the EIC.In ground floor.
195.7.b | 28.01 | (b) two coats.
196.7.b.i | 28.02 | (i) water based interior grade Acrylic primer.
|  |  | 1 | 66.03 | 1 |  | 66.03 | Sq.M
[6 empty] | Total | 66.03 | Sq.M | 4420 | %sqm | 2918.53
PWD(WB)/BUILDING WORKS/Page-196/Item-9
196.9 | 29 | Dry distempering to interior walls or ceiling, including cleaning washing smoothening surface.
196.9.b | 29.01 | (b) Two coat.
|  |  | 1 | 66.03 | 1 |  | 66.03 | Sq.M
[6 empty] | Total | 66.03 | Sq.M | 49 | Sq.M. | 3235.47
PWD(WB)/BUILDING WORKS/Page-196/Item-8
196.8 | 30 | Applying exterior grade Acrylic primer of approved quality and brand on plaster or concrete surface old or new surface to receive decorative textured (mat finish) or smooth finish acrylic exterior emulsion paint including scraping and preparing the surface throughly complete as per manufacturer's specification and as per direction of the EIC. In Ground Floor:.
196.8.b | 30.01 | (b) two coat.
|  |  | 1 | 57.7 | 1 |  | 57.7 | Sq.M
[6 empty] | Total | 57.7 | Sq.M | 4510 | %sqm | 2602.27
PWD(WB)/BUILDING WORKS/Page-197/Item-17
197.17 | 31 | Protective and decorative Acrylic exterior emulsion paint of approved quality , as per manufacture specification as per direction of EIC to be apply over Acrylic primer as required. the rate included cost of material , labour scaffoldic and all incidential charges but excluding the cost of primer.In ground floor ( two coat).
197.17.a | 31.01 | (a) Normal Acrylic emulaion.
|  |  | 1 | 57.7 | 1 |  | 57.7 | Sq.M
[6 empty] | Total | 57.7 | Sq.M | 67 | Sq.M. | 3865.9
PWD(WB)/BUILDING WORKS/Page-200/Item-1a
200.1a | 32 | (a) Priming one coat on steel or other metal surface with synthetic oil bound primer of approved quality including smoothening surfaces by sand papering etc.
|  |  | 1 | 5.64 | 1 |  | 5.64 | Sq.M
[6 empty] | Total | 5.64 | Sq.M | 29 | Sq.M. | 163.56
PWD(WB)/BUILDING WORKS/Page-200/Item-2
200.2 | 33 | (A) Painting with best quality synthetic enamel paint of approved make and brand including smoothening surface by sand parpering etc. in cluding using of approved putty etc. on the surface , if necessary.
200.2.a | 33.01 | (a) On timber or plastered surface: .
200.2.a.1 | 33.02 | (1) With super gloss (hi-gloss).
200.2.a.1.iv | 33.03 | (iv) Two coats (with any shade except white).
|  |  | 1 | 6.35 | 1 |  | 6.35 | Sq.M
[6 empty] | Total | 6.35 | Sq.M | 81 | Sq.M. | 514.35
PWD(WB)/BUILDING WORKS/Page-104/Item-13
104.13 | 34 | (a) M.S. or W.I. ornamental grill of approved design joints continuously welded with M.S., W.I. flats and bars for windows ,railing etc. fitted and fixed with necessary screws and lugs in ground floor. (Add extra @1% for each addl. floor up to 4th floor and @1.25% for each addl. floor above 4th floor).
104.13.i | 34.01 | (i) Grill weighing above 10 kg./sq.m.and up to 16kg/sq.m.
|  |  | 10 | 0.6 | 0.45 | 0.16 | 0.432 | Cu.M
|  |  | 5 | 0.6 | 0.6 | 0.16 | 0.288 | Cu.M
[6 empty] | Total | 0.72 | Cu.M | 10021 | Qntl. | 7215.12
PWD(WB)/BUILDING WORKS/Page-200/Item-1b
200.1b | 35 | (b) Priming one coat on timber or plastered surface with synthetic enamel oil bound primer of approved quality including smoothening surfaces by sand papering etc.
|  |  | 1 | 6.35 | 1 |  | 6.35 | Sq.M
[6 empty] | Total | 6.35 | Sq.M | 38 | Sq.M. | 241.3
PWD(WB)/BUILDING WORKS/Page-200/Item-2
200.2 | 36 | (A) Painting with best quality synthetic enamel paint of approved make and brand including smoothening surface by sand parpering etc. in cluding using of approved putty etc. on the surface , if necessary.
200.2.b | 36.01 | (b) On steel or other metal surface: .
200.2.b.1 | 36.02 | (1) With super gloss (hi-gloss).
201.2.b.1.iv | 36.03 | (iv) Two coats (with any shade except white).
|  |  | 1 | 5.64 | 1 |  | 5.64 | Sq.M
[6 empty] | Total | 5.64 | Sq.M | 79 | Sq.M. | 445.56
PWD(WB)/BUILDING WORKS/Page-66/Item-36
66.36 | 37 | Supplying and laying true to line and level vitrified tiles ofapproved brand (size not less than 600 mm X 600 mm X 10mm thick) in floor, skirting etc. set in 20 mm sand cementmortar (1:4) and 2 mm thick cement slurry back side of tilesusing cement @ 2.91Kg./sqM or using polymerised adhesive(6 mm thick layer applied directly over finished artificial stonefloor/Mosaic etc without any backing course) laid afterapplication slurry using 1.75 Kg of cement per sqM belowmortar only, joints grouted with admixture of white cementand colouring pigment to match with colour of tiles / epoxygrout materials of approved make as directed and removal ofwax coating of top surface of tiles with warm water andpolishing the tiles using soft and dry cloth upto mirror finishcomplete including the cost of materials, labour and all otherincidental charges complete true to the manufacturer'sspecification and direction of Engineer-in-Charge. (Whitecement, synthetic adhesive and grout material to be suppliedby the
contrr]e)I
66.36.II | 37.01 | (II) With Polymerised Adhesive [6 mm thick] & epoxygrouting materials for filling joints including spacer-2 mm[Applied directly over finished artificial stone floor/ mosaicetc.]
66.36.II.A |  | (A) Deep Colour & White
|  |  | 1 | 4.85 | 2.85 |  | 13.823 | Sq.M
[6 empty] | Total | 13.823 | Sq.M | 1789 | Sq.M. | 24729.35
PWD(WB)/BUILDING WORKS/Page-64/Item-35
64.35 | 38 | Supplying,Fitting & fixing 1st quality Ceramic tiles in walls and floors to match with the existing work & 4 nos. of key stones (10mm) fixed with araldite at the back of each tile & finishing the joints with white cement mixed with colouring oxide if required to match the colour of tiles including roughening of concrete surface, if necessary or by synthetic adhesive & grout materials etc.
64.35.B | 38.01 | (B) Wall With Sand Cement Mortar(1:3)15mm thick & 2 mm thick cement slurry at back side of tiles using cement @ 2.91 Kg/Sq.m. & joint filling using white cement slurry @0.20kg/Sq.m.
64.35.B.b | 38.02 | (b) Area of each tile the above 0.09Sq.m.
64.35.B.b.ii | 38.03 | (ii) Other than Coloured decorative including white.
|  |  | 2 | 7.675 | 2.1 |  | 32.235 | Sq.M
|  |  | 2 | 2.325 | 2.1 |  | 9.765 | Sq.M
|  |  | 4 | 1.6 | 2.1 |  | 13.44 | Sq.M
[6 empty] | Total | 55.44 | Sq.M | 1036 | Sq.M. | 57435.84
PWD(WB)/BUILDING WORKS/Page-233/Item-1
233.1 | 39 | Supplying profiles of requred section made of Aluminium Alloy extrusions conforming to IS:732-1983 and IS:1285-1975; Annodized (with required film thickness and specified colour/natural) matt finished conforming to IS: 1868-1983 for fabrication of composite door, sliding & casement windows, partitions, formed of basic sections of any ISI embossed/ certified make and brand as per direction of Engineer-In- Charge . (Payment will be made on finished length of the work).
233.1.A | 39.01 | (A) In 10-12 Micron thickness Annodizing film.
233.1.A.I | 39.02 | (I) Natural White.
234.1.A.I.h | 39.03 | (h) Louvered window.
234.1.A.I.h.i | 39.04 | (i) Top , bottom and side member.
|  |  | 1 | 6.5 |  |  | 6.5 | M
[6 empty] | Total | 6.5 | M | 183 | Meter. | 1189.5
PWD(WB)/BUILDING WORKS/Page-233/Item-1
233.1 | 40 | Supplying profiles of requred section made of Aluminium Alloy extrusions conforming to IS:732-1983 and IS:1285-1975; Annodized (with required film thickness and specified colour/natural) matt finished conforming to IS: 1868-1983 for fabrication of composite door, sliding & casement windows, partitions, formed of basic sections of any ISI embossed/ certified make and brand as per direction of Engineer-In- Charge . (Payment will be made on finished length of the work).
233.1.A | 40.01 | (A) In 10-12 Micron thickness Annodizing film.
233.1.A.I | 40.02 | (I) Natural White.
234.1.A.I.h | 40.03 | (h) Louvered window.
234.1.A.I.h.ii | 40.04 | (ii) Louver section.
|  |  | 1 | 7.2 |  |  | 7.2 | M
[6 empty] | Total | 7.2 | M | 658 | Meter. | 4737.6
PWD(WB)/BUILDING WORKS/Page-233/Item-1
233.1 | 41 | Supplying profiles of requred section made of Aluminium Alloy extrusions conforming to IS:732-1983 and IS:1285-1975; Annodized (with required film thickness and specified colour/natural) matt finished conforming to IS: 1868-1983 for fabrication of composite door, sliding & casement windows, partitions, formed of basic sections of any ISI embossed/ certified make and brand as per direction of Engineer-In- Charge . (Payment will be made on finished length of the work).
233.1.A | 41.01 | (A) In 10-12 Micron thickness Annodizing film.
233.1.A.I | 41.02 | (I) Natural White.
233.1.A.I.e | 41.03 | (e) Casement window (40mm. Depth series).
233.1.A.I.e.v | 41.04 | (v) Cleat angle. (Non-annodozed).
|  |  | 1 | 6.48 |  |  | 6.48 | M
[6 empty] | Total | 6.48 | M | 263 | Meter. | 1704.24
PWD(WB)/BUILDING WORKS/Page-243/Item-9
243.9 | 42 | Supplying bubble free float glass of approved make and brand. Conforming to IS: 2835-1987.
243.9.iv | 42.01 | (iv) 5 mm thick coloured / tinted / smoke glass.
|  |  | 1 | 1.08 | 1 |  | 1.08 | Sq.M
[6 empty] | Total | 1.08 | Sq.M | 585 | Sq.M. | 631.8
PWD(WB)/BUILDING WORKS/Page-268/Item-17
268.17 | 43 | Painting block letters or digits in Black Japan or any approved point as per direction.
268.17.v | 43.01 | (e) Size above 7.5 cm. and upto 10. cm.
|  |  | 450 |  |  |  | 450 | No.
[6 empty] | Total | 450 | No. | 12 | each | 5400
PWD(WB)/BUILDING WORKS/Page-261/Item-9
261.9 | 44 | Supplying and Planting of different plant /trees ( Supplying well grown plants bushy and healthy, minimum height as specified i.e.exposed height including all leads & lift,carriage, handling, manuring, applying presticide and fertilizer etc.
261.9.i | 44.01 | i) Furcaria veriegated 10-12 leaves in height 20-30cm in earthen pots of size 25cm.
|  |  | 10 |  |  |  | 10 | No.
[6 empty] | Total | 10 | No. | 162 | Each | 1620
PWD(WB)/BUILDING WORKS/Page-261/Item-9
261.9 | 45 | Supplying and Planting of different plant /trees ( Supplying well grown plants bushy and healthy, minimum height as specified i.e.exposed height including all leads & lift,carriage, handling, manuring, applying presticide and fertilizer etc.
261.9.x | 45.01 | x) Ficus blakii ( F. Vivicon ) well branched (Bushy ) of height 120cm - 135 cm in earthen pot of size 30cm.
|  |  | 3 |  |  |  | 3 | No.
[6 empty] | Total | 3 | No. | 187 | Each | 561
PWD(WB)/BUILDING WORKS/Page-261/Item-9
261.9 | 46 | Supplying and Planting of different plant /trees ( Supplying well grown plants bushy and healthy, minimum height as specified i.e.exposed height including all leads & lift,carriage, handling, manuring, applying presticide and fertilizer etc.
262.9.xxvi | 46.01 | xxvi) Areca Palm 4 - 5 suckers of height 90cm to 105 cm in earthen pots of size 25 cm.
|  |  | 3 |  |  |  | 3 | No.
[6 empty] | Total | 3 | No. | 127 | Each | 381
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-79/Item-4
79.4 | 47 | Supplying, fitting and fixing Orissa pattern water closet in white glazed vitreous chinaware of approved make in position complete excluding 'P' or 'S' trap (excluding cost of concrete for fixing).
79.4.i | 47.01 | 580 mm X 440 mm.
|  |  | 5 |  |  |  | 5 | No.
[6 empty] | Total | 5 | No. | 1613 | Each | 8065
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-80/Item-6
80.6 | 48 | Supplying, fitting and fixing Flat back urinal (half stall urinals) in white vitreous chinaware of approved make in position with brass screws on 75 mm X 75 mm X 75 mm wooden blocks complete.
80.6.ii | 48.01 | 470 mm X 280 mm X 340 mm.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 945 | Each | 1890
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-80/Item-7
80.7 | 49 | Supplying, figging and fixing Squating plate with integral flushing in white vitreous chinaware of approved make in cement concrete(6:3:1) with jhama chips complete.(Payment of concrete will be paid seperately).
80.7.i | 49.01 | 450 mm X 350 mm.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 881 | Each | 1762
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-36/Item-2
36.2 | 50 | Supplying, fitting and fixing 10 litre P.V.C. low-down cistern conforming to I.S. Specification with P.V.C. fittings complete, C.I. brackets including two coats of painting to bracket etc.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 1015 | Each | 2030
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-81/Item-11
81.11 | 51 | Supplying, fitting and fixing 32 mm dia. flush pipe of approved make with necessary fixing materials and clamps complete.
81.11.i | 51.01 | Polythene Flush Pipe.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 155 | Each | 310
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-81/Item-12
81.12 | 52 | Supplying, fitting and fixing urinals flush pipe fittings of approved brand.
81.12.a | 52.01 | C.P. urinals flush pipe fiitngs range of one .
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 414 | Each | 828
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-41/Item-2
41.2 | 53 | Supplying, fitting and fixing white vitreous china best quality approved make wash basin with C.I. Brackets on 75 mm X 75mm wooden blocks, C.P. waste fittings of 32 mm dia., one approved quality brass C.P. pillar cock of 15 mm dia., C.P. chain with rubber plug of 30mm dia, approved quality P.V.C.waste pipe with C.P. nut 32mm dia., 900 mm long approved quality P.V.C. connection pipe with heavy brass C.P.nut including mending good all damages and painting the brackets with two coats of approved paint.
41.2.ii | 53.01 | 550 mm x 400 mm size.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 2208 | Each | 4416
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-41/Item-3
41.3 | 54 | Supplying, fitting and fixing pedestal of approved make for wash basin.(White).
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 1497 | Each | 2994
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-43/Item-9
43.9 | 55 | Supplying, fitting & fixing approved brand P.V.C. CONNECTOR white flexible, with both ends coupling with heavy brass C.P.nut, 15mm dia.
43.9.iii | 55.01 | 600 mm long.
|  |  | 5 |  |  |  | 5 | No.
[6 empty] | Total | 5 | No. | 107 | Each | 535
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-43/Item-10
43.10 | 56 | Supplying, fitting and fixing approved brand 32mm dia P.V.C. waste pipe, with PVC coupling at one end fitted with necessary clamps.
43.10.iv | 56.01 | 1050mm long.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 91 | Each | 182
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-3/Item-3
3.3 | 57 | Supplying, fitting and fixing shower of approved brand and make.
3.4.f | 57.01 | Hand shower(Health Faucet) with 1mtr Fexible Tube with wall Hook (Equivalent to code No.573 & Model-ALLIED of Jaquar or Similar)
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 1251 | Each | 2502
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-6/Item-7
6.7 | 58 | Supplying, fitting and fixing bib cock or stop cock.
6.7.a-i | 58.01 | Chromium plated Bib Cock short body (Equivelent to Code No.511 & Model- Tropical /sumthing special of ESSCO or Similar brand).
|  |  | 5 |  |  |  | 5 | No.
[6 empty] | Total | 5 | No. | 539 | Each | 2695
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-6/Item-7
6.7 | 59 | Supplying, fitting and fixing bib cock or stop cock.
6.7.b-i | 59.01 | Chromium plated Stop Cock (Equivelent to Code No.513(A) & 513(B) Model- Tropical /sumthing special of ESSCO or Similar brand).
|  |  | 3 |  |  |  | 3 | No.
[6 empty] | Total | 3 | No. | 493 | Each | 1479
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-6/Item-7
6.7 | 60 | Supplying, fitting and fixing bib cock or stop cock.
6.7.d-i | 60.01 | Chromium plated plated angular Stop Cock with wall flange (Equivelent to Code No.5053 & Model- Florentine of Jaquar or Similar brand).
|  |  | 3 |  |  |  | 3 | No.
[6 empty] | Total | 3 | No. | 815 | Each | 2445
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-45/Item-19
45.19 | 61 | Supplying, fitting and fixing pillar cock of approved make.
45.19-a.i | 61.01 | CP Pillar Cock-15 mm. (Equivalent to Code No.507 & Model-Tropical/Sumthing Special of ESSCO or similar brand).
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 555 | Each | 1110
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-12/Item-19-I
12.19-I | 62 | Supplying, fitting and fixing PVC pipes of approved make of of Schedule 80 (medium duty) conforming to ASTMD-1785 and threaded to match with GI Pi;es as per IS:1239 (Part-I) with all necessary accessories, specials viz. socket, bend, tee, union, cross, elbo, nipple, longscrew, reducing socket, reducing tee, short piece etc. fitted with holder bats clamps, including cutting piles, making threads, fitting, fixing etc. complete in all respect including cost of all necessary fittings as required, jointing materials and two coats of painting with approved paint in any position above ground. (Payment will be made on the centre line measurements of total pipe line including all specials. No separate payment will be made for accessories, specials. Payment for painting will be made seperately).
12.19-1.a | 62.01 | For Exposed Work PVC Pipes.
12.19-1.a.iii | 62.02 | 25 mm.
|  |  | 1 | 15 |  |  | 15 | M
[6 empty] | Total | 15 | M | 177 | Mtr. | 2655
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-12/Item-19-I
12.19-I | 63 | Supplying, fitting and fixing PVC pipes of approved make of of Schedule 80 (medium duty) conforming to ASTMD-1785 and threaded to match with GI Pi;es as per IS:1239 (Part-I) with all necessary accessories, specials viz. socket, bend, tee, union, cross, elbo, nipple, longscrew, reducing socket, reducing tee, short piece etc. fitted with holder bats clamps, including cutting piles, making threads, fitting, fixing etc. complete in all respect including cost of all necessary fittings as required, jointing materials and two coats of painting with approved paint in any position above ground. (Payment will be made on the centre line measurements of total pipe line including all specials. No separate payment will be made for accessories, specials. Payment for painting will be made seperately).
12.19-1.a | 63.01 | For Exposed Work PVC Pipes.
12.19-1.a.i | 63.02 | 15 mm dia.
|  |  | 10 | 1 |  |  | 10 | M
[6 empty] | Total | 10 | M | 101 | Mtr. | 1010
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-12/Item-19-I
12.19-I | 64 | Supplying, fitting and fixing PVC pipes of approved make of of Schedule 80 (medium duty) conforming to ASTMD-1785 and threaded to match with GI Pi;es as per IS:1239 (Part-I) with all necessary accessories, specials viz. socket, bend, tee, union, cross, elbo, nipple, longscrew, reducing socket, reducing tee, short piece etc. fitted with holder bats clamps, including cutting piles, making threads, fitting, fixing etc. complete in all respect including cost of all necessary fittings as required, jointing materials and two coats of painting with approved paint in any position above ground. (Payment will be made on the centre line measurements of total pipe line including all specials. No separate payment will be made for accessories, specials. Payment for painting will be made seperately).
12.19-1.b | 64.01 | For Concealed Work.
12.19-1.b.i | 64.02 | 15 mm.
|  |  | 10 | 1 |  |  | 10 | M
[6 empty] | Total | 10 | M | 137 | Mtr. | 1370
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-5/Item-5
5.5 | 65 | Supplying, fitting and fixing gunmetal wheel valve of approved brand and make tested to 21 kg sq.cm. (for water lines only).
5.5.vii | 65.01 | 25 mm.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 778 | Each | 1556
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-37/Item-6
37.6 | 66 | Supplying PVC water storage tank of approved quality with closed top weith lid (Black) - Multilayer.
37.6.b | 66.01 | 1000 litre capacity.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 5128 | Each | 10256
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-37/Item-10
37.10 | 67 | Labour for hoisting plastic water storage tank.
37.10.i | 67.01 | Upto 1500 litre capacity.
37.10.i.a | 67.02 | Upto 1st story from G.L.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 96 | Each | 192
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-38/Item-13
38.13 | 68 | Labour for punching hole in plastic water storage tank upto 50 mm dai.
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 19 | Each | 76
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 69 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
68.23-A.i | 69.01 | Single socketed 3 meter length.
69.23-A.i.b | 69.02 | 110 mm.
|  |  | 30 | 1 |  |  | 30 | M
[6 empty] | Total | 30 | M | 292 | Mtr. | 8760
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 70 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 70.01 | Fittings.
70.23.B.i | 70.02 | Coupler.
70.23.B.i.b | 70.03 | 110 mm.
|  |  | 8 |  |  |  | 8 | No.
[6 empty] | Total | 8 | No. | 85 | Each | 680
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 71 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 71.01 | Fittings.
70.23.B.ii | 71.02 | Plain tee.
70.23.B.ii.b |  | 110 mm.
|  |  | 12 |  |  |  | 12 | No.
[6 empty] | Total | 12 | No. | 85 | Each | 1020
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 72 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 72.01 | Fittings.
70.23.B.iii | 72.02 | Door Tee.
70.23.B.iii.b |  | 110 mm.
|  |  | 10 |  |  |  | 10 | No.
[6 empty] | Total | 10 | No. | 195 | Each | 1950
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 73 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 73.01 | Fittings.
71.23.B.ix | 73.02 | Bend 45o.
71.23.B.ix.b |  | 110 mm.
|  |  | 10 |  |  |  | 10 | No.
[6 empty] | Total | 10 | No. | 89 | Each | 890
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 74 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 74.01 | Fittings.
71.23.B.xi | 74.02 | Door Bend (T.S).
71.23.B.xi.b |  | 110 mm.
|  |  | 7 |  |  |  | 7 | No.
[6 empty] | Total | 7 | No. | 147 | Each | 1029
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 75 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 75.01 | Fittings.
71.23.B.xvi | 75.02 | Pipe Clip.
71.23.B.xvi.b |  | 110 mm.
|  |  | 30 |  |  |  | 30 | No.
[6 empty] | Total | 30 | No. | 21 | Each | 630
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 76 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 76.01 | Fittings.
71.23.B.xvii | 76.02 | W.C. Connector (150m m long) 125 X 110 (W/WC Ring) 75 mm. .
|  |  | 4 |  |  |  | 4 | No.
[6 empty] | Total | 4 | No. | 142 | Each | 568
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 77 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 77.01 | Fittings.
72.23.B.xxxi | 77.02 | Plain Floor Trap with Top tile and Stainer. 75mm..
|  |  | 7 |  |  |  | 7 | No.
[6 empty] | Total | 7 | No. | 144 | Each | 1008
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 78 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
70.23.B | 78.01 | Fittings.
73.23.B.l | 78.02 | Rubber Ring.
73.23.B.l.b | 78.03 | 110 mm.
|  |  | 15 |  |  |  | 15 | No.
[6 empty] | Total | 15 | No. | 17 | Each | 255
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 79 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
74.23.C | 79.01 | Rubber Lubricant. 500 ML.
|  |  | 1 |  |  |  | 1 | No.
[6 empty] | Total | 1 | No. | 187 | Each | 187
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-68/Item-23
68.23 | 80 | Supply of UPVC pipes (B Type) & fittings conforming to IS-13592-1992 .
74.23.D | 80.01 | Solvent Cement. 250 ML.
|  |  | 1 |  |  |  | 1 | No.
[6 empty] | Total | 1 | No. | 103 | Each | 103
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-74/Item-24
74.24 | 81 | Labour for fitting and fixing U.P.V.C. pipes for above ground work including cost of jointing materials etc. fitting and fixing all necessary specials, cutting pipes, cutting holes in walls or R.C. floor where necessary and mending good all damages excluding the cost of masonry or concrete work, if necessary, but including the cost and fitting and fixing holder bat clamps (any foor) or for underground work including cutting trenches upto 1.5 metre and refilling the same complete as per direction of the Enginer-in-charge) Payment will be made on centre line measurement of the total pipeline including specials.).
74.24.B | 81.01 | Underground.
74.24.B.ii |  | 110 mm dia.
|  |  | 20 | 1 |  |  | 20 | M
[6 empty] | Total | 20 | M | 84 | metre | 1680
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-87/Item-1
87.1 | 82 | Constructing Inspection pit of inside measurement 600mm X 600mm X upto 600mm(depth) with 250 mm thick 1st. class brick work in cement mortar(4:1) on all sides, bottom of the pit consisting of 100 mm thick cement concrete(1:6:3) with stone chips over a layer of jhama brick flat soiling, 15 mm thick (1:4) cement plaster to inside walls and outside walls upto G.L. and 20 mm thick(1:4) plaster to bottom of the pit, providing necessary invert with cement concrete(1:3:6) with stone chips as per direction, neat cement finishing to entire internal surfaces, top of the pit covered with 100mm thick R.C.C. slab (1:1.5:3) with stone chips and necessary reinforcements upto 1% and shuttering including 6 mm thick cement plaster(1:4) in all external surfaces of the slab and one 560 mm dia. R.C.C. manhole cover of approved make supplied, fitted and fixed in the slab with necessary fittings, necessary earthwork in excavation in all sorts of soil, filling sides of the pit with earth and removing spoils
after work complete in all respect with all costs of labour and materials.
87.1.ii | 82.01 | With Bazree (Pakur Variety).(SAIL/TATA/RINL)
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 6434 | each | 12868
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-88/Item-3
88.3 | 83 | Construction of Septic tank of different capacities as per approved drawing with 1st class brick work in cement mortar (4:1) including two 560 mm dia. R.C.C. manhloe cover of approved make supplied, fitted and fixied in the top slab with necessary fittings, 19 mm thick cement plaster(4:1) with neat cement finish to the internal surfaces and 12 mm thick plaster(4:1) to outside wall upto 200 mm below G.L. floor finished with 25 mm thick grey artificial stone including supplying, fitting and fixing all necessary specials, fittings, S.W. tees, C.I. foot rest etc. including excavating earth in all sorts of soil, shoring, bailing and pumping out water as necessary, ramming, dressing the bed and refilling the sides of the tank with earth, removing spoils, fliing up the chamber with clear water, removing foreign materialsfrom the chamber and including constructing attached inspection pit as per approved dawing and connecting all necessary pipes, joints etc. with internal plaster work and artif
icial stone flooring is to be done with admixture of water proofing compound @ 5% by weight of cement, complete in all respect as per directon of Engineer-in-Charge.
89.3.iii | 83.01 | For 30 users.
89.3.iii.B | 83.02 | With Bazree (N.B.Variety).(SAIL/TATA/RINL)
|  |  | 1 |  |  |  | 1 | No.
[6 empty] | Total | 1 | No. | 57267 | Each | 57267
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-89/Item-4
89.4 | 84 | Construction of circular soak well 2.5 metre deep in all types of sandy soils with dry brick work upto 1.6 metre from the bottom having 150 mm intermediate cement brick work(6:1) band all round and cement brick work(6:1) upto 0.90 metre from top with 19 mm thick cement plastering(4:1) to inside face upto the depth of cement brick work, 12 mm thick cement plaster(4:1) on top of the R.C.C. cover slab including filling bottom 1.00 metre of inside of the well with brick metal(50 mm to 63 mm size) including R.C.C. cover slab of designed thickness with cement concrete(4:2:1) with stone chips with necessary reinforcement and shuttering including one 560 mm dia. R.C.C. manhole cover of approved make supplied, fitted and fixed in the cover slab with necessary fittings, making necessary arrangements for pipe conections, excavation of well including shoring, dewatering and remeving the excess earth from the premisis as per direction complete in all respect with all costs of labour and materials.W
ith 250 mm thick dry brick work and 250 mm thick cement brick work(6:1) and 1.00 m. inside dia.
89.4.A | 84.01 | (SAIL/TATA/RINL)
|  |  | 1 |  |  |  | 1 | No.
[6 empty] | Total | 1 | No. | 15532 | Each | 15532
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-82/Item-22
82.22 | 85 | Supplying, fitting and fixing towel rail with two brackets.
82.22.a | 85.01 | C.P. over brass.
82.22.a.ii | 85.02 | 25 mm dia. and 600 mm long.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 430 | Each | 860
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-81/Item-15
81.15 | 86 | Supplying, fitting and fixing bevelled edge mirror 5.5 mm thick silver red as per I.S. 3438/1965 together with brass C.P. hinges.
81.15.ii | 86.01 | 600 mm X 450 mm.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 484 | Each | 968
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-82/Item-18
82.18 | 87 | Supplying, fitting and fixing soap holder.
82.18.b | 87.01 | Fibre glass.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 58 | Each | 116
PWD(WB)/SANITARY AND PLUMBING WORKS/Page-81/Item-16
81.16 | 88 | Supplying, fitting and fixing glass shelf with aluminium guard rails.
81.16.a | 88.01 | Ordinary type with 5.5 mm sheet glass.
82.16.a.i | 88.02 | 450 mm X 125 mm.
|  |  | 2 |  |  |  | 2 | No.
[6 empty] | Total | 2 | No. | 341 | Each | 682
[6 empty] | TOTAL AMOUNT |  |  |  |  | 569889.15
[6 empty] | 18 | % GST on Total Amount |  |  |  | 102580.05
[6 empty] | Sub - Total 1 (Total Amount + GST) |  |  |  |  | 672469.2
[6 empty] | 3 | % Contigency on Sub-Total 1 |  |  |  | 20174.08
[6 empty] | Sub - Total 2 (Sub - Total 1 + contigency) |  |  |  |  | 692643.28
[6 empty] | Labour Welfare Cess 1% on Sub-Total 1 |  |  |  |  | 6724.69
[6 empty] | Grand total |  |  |  |  | 699367.97
[6 empty] | Say |  |  |  |  | 699368
(Rupees six lakh ninety nine thousand three hundred sixty eight) only